## Aug 24 - 28
Weekly Project Workload Report
Year | 2015
Week | Aug 24 - 28
PIC | Project Name | Project Type | Project Source/Referral | Contract Amount | Existing Stage | Weekly Total Effort (in MD) | Cumulative Total Effort (in MD) | Remark
Dante | StarLite | Tailor-made Website with CMS [Responsive] | Sales Team - Jack Yeung | 223802 | 2nd Phrase - Initial | 0 | 23.5
Dante | Orient Fair Development Ltd | Enhancment | JB Team - Bryan Poon | 183200 | UAT Stage | 0.5 | 8
Dante | Tom Lee Music Co. Ltd | Tailor-made Website with CMS [Responsive] | JB Team - Daniel Fong | 191250 | UAT Stage | 1 | 8.25
Dante | Modern Terminals Limited | Tailor-made Website with CMS | PS Team - Stephen Tam | 214000 | UAT Stage | 1 | 34.625
Dante | Private Shop | Template Website with CMS [Responsive] | Sales Team - Jack Yeung | 39800 | UAT Stage | 1 | 15
Dante | CPCS | E-Shop Apps [Testing purpose] | TBC | TBC | UAT Stage | 0.5 | 3
Dante | Pine Way Enterprise Limited | Tailor-made Website with CMS [Responsive] | Franco Tsoi | TBC | Pre-Sales | 1 | 2
Heidi | Sun Shine Property Consultant | Tailor Made Website + CMS | Bryan | 95955 | UAT | 0.2 | 19.2 | Waiting client to comment on UAT
Heidi | BuyHome.hk | ERP Project | Luke | 88000 | UAT | 2.8 | 19.6 | Keep revising and studying some new requests needed to be quoted
Heidi | Food Beauty Paradise | Website revamp | Internal Project | - | UAT | 0.5 | 7.5 | Floor plan design has confirmed, banner design has sent
Heidi | Loreal HK Ltd | Minisite | Heidi | 21800 | Design | 0 | 4 | Design Stage, waiting client to legal approve
Heidi | SCAA | Tailor Made Website + CMS | Jobi | 78000 | Program | 1.3 | 3.2 | Soft launched. Working on Chinese Version
Livia | FSEE | Apps development | Jobi Wong | 187500 | API | 0.8 | 19.4
Livia | Miele | Minisite with Game | Leslie | N/A | Design | 0.3 | 4.2
Livia | Zespri | Talior made website | Stanley | 20000 | UAT | 0.8 | 2.5 | CMS revision
Livia | Nutri Green | Content update | Livia | 6400 | Initial | 0.1 | 0.6
Livia | Bioessence | Tailormade Website | Phoebe | 48000 | UAT | 0.7 | 1.7
Livia | Prosperity | Tailormade Website | Dennis | 21020 | UAT | 0.4 | 1.2 | content update and CMS revision
Livia | ikasa | Tailormade Website | Jack | 25600 | UAT | 0.2 | 0.7
Livia | Easy Creation Asia | Enhancement | Daniel Fong | 4500 | Initial | 0.3 | 0.3
Xavier | HKBU Estate Office - Low Carbon | Website Revamp | Sales Team - Donald | 38000 | Design | 0.0625 | 7.4375 | Inner page design waiting for comments.
Xavier | D&B | Custom Website | Previous Project - Daniel Ip | 153297.5 | Maintenance | 1.375 | 29.4375 | Phase 1 User Guide prepared. Training session confirmed.
Xavier | Times | Custom Website | Previous Project - Daniel Ip | 100000 | UAT | 0.0625 | 25.375 | Urging client for settlement.
Xavier | CPCS | Mobile App Development | Luke | 108000 | Programming | 1.5 | 46.125 | Client PayPal account issue to be resolved. Phase 2 Push / Recipe UI sent out with comments returning.
Xavier | HKBU - AAO | Maintenance | Previous Project - Wing Cheung | 29025 | Maintenance | 0.125 | 18.4375 | Got Sept issue schedule and materials to start.
Xavier | SBC International | Mobile App Development | Sales Team - Alfee | 130000 | UAT | 0.0625 | 16.875 | Agreed with client to split 3rd payment into 50/50.
Xavier | EDE Online | Custom Website | Sales Team - Alfee | 52500 | UAT | 0.0625 | 3.25 | Still waiting for payment.
Xavier | Yukzhi | Custom Website | Jobi Wong | 17600 | Programming | 0 | 2.875 | Wait for client to supply last set of image changes.
Xavier | FSEE | Mobile App Development | Solution Sales Team - Franco Tsoi | 210000 | Programming | 0.75 | 16.0625 | Con call to discuss with API. 1st app internal testing.
Xavier | Swissnatuerlich | Custom Website | Previous Project - Jobi Wong | 49000 | 2nd Language | 0.0625 | 1.3125 | Testing in progress.
Xavier | Neptune | Maintenance | Previous Project - Jobi Wong | 35000 | Maintenance | 0 | 0.5 | No update this week.
Xavier | HKBU Estate Office - BUGS | Maintenance | Sales Team - Donald | 8550 | Maintenance | 0 | 0.1875 | No response from client.
Xavier | Overlander | Mobile App Development [Internal Testing] | JB Team - Bryan Poon | 169180 | Programming | 0 | 0.25 | No testing this week.
[5 empty] | Total: | 17.4625 | 346.6